## Sheet1
Agile Group 9 - Sprint 1 | [7 empty] | Members: | Roles:
Sprint Date: 25/01/21 - 29/01/21 | [7 empty] | Gina Fenton | Scrum Master
[8 empty] | Timothy Lundberg | Product Owner
Goal: Demonstrate the ability for researches to curate questionairres and export data from answered ones. | [7 empty] | Laura Hutchison | Developer
[8 empty] | Calum Parsons | Developer
Initial Velocity = 11 | [7 empty] | Shanna Balfour | Developer
[8 empty] | Ema Anicic | Developer
[8 empty] | Michael Olori | Developer
[8 empty] | Shaun Yap | Developer
Stories for this sprint:
User Story: |  |  | Acceptance Crit: |  | Member: |  | Points: | Done? (DoD) | Accepted?
As a researcher, I want to be able to add any questionnaires I have designed to my application so that they can get approval |  |  | If a created questionairre can be attached to an email then accept |  | Shaun, Tim |  | 2 | Y/N | Y/N
As a researcher, I want to be able to export data from the questionnaire so that the data can be used for analysis. |  |  | All of the questionairre responses can be downloaded in an accessible and easily processible format |  | Shanna |  | 2
As a stakeholder, I want participants to only have access to questionnaires so that the rest of the experiment is private and safe |  |  | When participants log in, they will only have access to questionnaires on their homepage. |  | Laura + Michael |  | 2
As a researcher I want to be able to send questionnaires for participants to fill in so I can collect data from users |  |  | Researchers are able to send specific questionnaires to specific participants |  | Gina |  | 2
As a researcher, I want the ability to create a questionnaire so that they can be sent to users. |  |  | Questionnaires can be designed or processed by the program into its own suitable format |  | Ema, Calum |  | 3
Other Tasks: Not Stories, but still need done |  |  | Member: |  | Done?
Definition of Done:
Set up database stuff so we can access it! |  |  | Laura + Michael |  |  |  |  | -Meets accessibility guidelines -Code has been reviewed -Meets acceptance test for story -Product Owner accepts story
Set up a visual studio c# .net application that works on web |  |  | Ema + Calum + Timothy |  | Yes! 27/01/21
Scrum Minutes
Date | Happiness | Yesterday Progress |  | Issues |  | Today's Work Plan
example date | 4 :) 3 :¦ 1 :(
2021-01-26 | 4 Spirits, 1 Mock, 2 Beer | - Lots of research done into best way to host the software |  | - undertanding visual studio - feeling lost with where to start |  | -database setup -github setup - everyone able to work comfortably
2021-01-27 | 2 m, 5 b, 1 s | -Azure is now up and running our test code |  | -had to change github repo to get it to work |  | - need to know how to develope web application with asp.net - find resources for this
mocktail (happy) beer (ok still) spirit (getting bad) industrial strength (uh oh)
M,B,S,I
daily scrum shouldn't cover the technicalities of work, it should focus on the next steps to solve problems and help keep things moving - technicalities can be done at other times aside from the scrum