## Sheet1
Sprint 2 | [7 empty] | Members: | Roles:
Sprint Date: 01/02/21 - 05/01/21 | [7 empty] | Gina Fenton | Scrum Master
[8 empty] | Timothy Lundberg | Product Owner
Goal: Demonstrate the ability for researches to curate questionairres and export data from answered ones. | [7 empty] | Laura Hutchison | Developer
[8 empty] | Calum Parsons | Developer
Initial Velocity = 7 | [7 empty] | Shanna Balfour | Developer
[8 empty] | Ema Anicic | Developer
[8 empty] | Michael Olori | Developer
[8 empty] | Shaun Yap | Developer
Stories for this sprint:
User Story: |  |  | Acceptance Crit: |  | Member: |  | Points: | Done? (DoD) | Accepted?
As a principal researcher, I want full access to my own experiments so that I can view and keep track of all the relevant data/progress at any time. |  |  | When researcher logs in they can see all of their questionnaires in one place, as well as data about it |  | NOT AN ACTIVE STORY UNLESS LATER WE NEED MORE VELOCITY |  | N/A | N/A | N/A
2. As a researcher, I want to be able to export data from the questionnaire so that the data can be used for analysis. |  |  | All of the questionairre responses can be downloaded in an accessible and easily processible format |  | Timothy, Laura |  | 2 | N
(removed story #9 as it is more of an acceptance test than an independant story)
4. As a researcher I want to be able to send questionnaires for participants to fill in so I can collect data from users |  |  | Researchers are able to send specific questionnaires to specific participants |  | Gina, Ema |  | 2 | N
5. As a researcher, I want the ability to create a questionnaire so that they can be sent to users. |  |  | Questionnaires can be designed or processed by the program into its own suitable format |  | Shaun, Cally, Laura |  | 3 | N
Other Tasks: Not Stories, but still need done |  |  | Member: | Story | Done?
[6 empty] | Definition of Done: |  |  | Developer Tasks (each story broken down to steps to identify tasks)
Create login page |  |  | Shanna, Gina |  |  | -Meets accessibility guidelines -Is UoD branded -Code has been reviewed -Meets acceptance test for story -Product Owner accepts story -Only those authorised can access this feature |  |  | Story 2: | Story 3: | Story 4: | Story 5: | Story 6 Idea
Create questionnaire page (show author, title, date etc) |  |  | Cally, Michael | [5 empty] | 1. researcher logins | 1. no other pages can be accessed w/o login | 1. researcher logins | 1. researcher logs in | - project page, w all related stuff under each heading
Export curated questionairres into JSON (process JSONs from database) |  |  | Laura
Turn stored medium text into CSV file that can be downloaded with button/(after storing answers in database) |  |  | Timothy | [5 empty] | 2. chooses a questionairre from home page |  | 2. selects questionairre and selects send | 2. selects questionairre designer page
Send questionairre' page |  |  | Gina, Ema |  | Yes, 01/02/21 - page done, need questionnaires to send |  |  |  | 3. view questionairre page (show q's) |  | 3. they access the questionairre with the link alone | 3. enter number of authors + titles, add sections, add questions to each section and type of question
Curated questionairres have their unique link |  |  | later scrum : ) | [5 empty] | 4. researches exports database results into csv |  |  | 4. clicks create and the system adds the curation to the database
Question designer page |  |  | Shaun, Cally
Turn database design into SQL table |  |  | Laura
Adding aesthetic value |  |  | Cally
Logins on the SQL stuff (views?) |  |  | Ema
mocktail (happy) beer (ok still) spirit (getting bad) industrial strength (uh oh)
Scrum Minutes
Date | Happiness | Yesterday Progress |  | Issues/Impediments |  | Today's Work Plan
example date | M,B,S,I
2021-02-01 | 2M, 5.5B, 0.5S | Yesterday we planned this sprint |  | Not many yet! Possible internet issues |  | - Get sendquestionairre integrated - Get login page setup - Work on frontend questionairre builder -SQL CSV transpose
2021-02-02 | 2M, 5b, 1S | Send questionnaire done! Just need actual 'questionnaires' to send |  | Possible internet issues, inexperience with cshtml and html for some members |  | - Get new entity framework pushing and pulling database stuff - Work on design stuff - Work on remaining web pages |  | daily scrum shouldn't cover the technicalities of work, it should focus on the next steps and help keep things moving - technicalities can be done at other times aside from the scrum