## Sheet1
User Story | Github No. | Story Points | Priority- (Highest, Above Average, Average, Below Average, Lowest) |  | Category/Path
As a lab manager, I want access to everything in the lab system and to have the ability to manage users so that I can monitor the experiments and workers | #24 | 5 | Above Average |  | Management
As a principal researcher, I want full access to my own experiments so that I can view and keep track of all the data/progress at any time. | #19 | 3 | Above Average |  | Management
As a researcher I want relationships between quotes generated, with 3-4 similar quotes becoming ‘super themes’ so that I can understand important themes and perform useful analysis | #13 | 8 | Above Average |  | Management
As a researcher I want to be able to send questionnaires for participants to fill in so I can collect data from users. | #3 | 2 | Above Average | Sprint 1 | Quiz
As a researcher, I want the ability to create a questionnaire so that they can be sent to users. | #2 | 3 | Above Average | Sprint 1 | Quiz
As a researcher, I want to be able to export data from the questionnaire so that the data can be used for analysis | #14 | 2 | Above Average | Sprint 1 | Quiz
As a researcher, I want to be able to generate a transcript from audio files so that it can be used for data analysis | #4 | 2 | Above Average |  | Analysis
As a researcher, I want to give users the ability to give feedback as they are performing a task such as a website utility, to get a better understanding of the use of the system. | #8 | ? | Above Average |  | Analysis
As a stakeholder, I want participants to only have access to questionnaires so that the rest of the experiment is private and safe. | #9 | 2 | Above Average | Sprint 1 | Quiz
As a co-researcher, I want only access to the parts the principal researcher says I need access to so that I can perform tasks I need to and not be distracted with irrelevant areas. | #23 | 3 | Average |  | Management
As a researcher, I want the ability to Identify interesting quotes from a transcript and attach tags (called themes) so that these quotes can easily be found. | #20 | 3 | Average |  | Analysis
As a stakeholder, I want the software to be certified and have university branding so that the users feel secure using it. | #16 | ? | Average |  | Design
As a researcher I want to get some visualisations of the data to understand it better. | #17 | 5 | Below Average |  | Anlaysis
As a researcher, I want the ability to manage the schedules of participants so that their matching data can be ready for them when they are partaking in the experiments | #25 | 5 | Below Average |  | Management
As a researcher, I want the ability to record video and webcam footage while the user is visiting a website to improve analysis on data. | #18 | 5 | Below Average |  | Analysis
As a researcher, I want the ethics application process to automatically provide me the correct forms so that the process is streamlined and hassle free. - product owner take to client and ask if this would work for ‘making the ethics process easier’ | #12 | 2 | Below Average |  | Ethics
As a researcher, I want to be able to send users any consent forms or other similar forms that they will need to fill out, so I can add them to my application. | #21 | 2 | Below Average |  | Ethics
As a researcher, I want to have a process for documenting interesting moments during the recording of a participant, so that I don’t have to go through the entire tape every time I perform analysis. | #5 | 3 | Below Average |  | Analysis
As a researcher, I want an easier way of matching up footage timestamps (of 3 cameras) so I can save time and effort. | #10 | ? | Lowest |  | Analysis
As a researcher, I want the system to alert me when there is an audio spike in a video that could indicate an interesting event (such as a user bumping into an object) so I can go back to check if that audio correlates to an interesting event in the video | #11 | 5 | Lowest |  | Analysis
As a researcher, I want to be able to add any questionnaires I have designed to my application so that they can get approval | #15 | 2 | Lowest | Sprint 1 | Quiz
As a researcher, I want to be able to read the University of Dundee’s “Code of Practice for Non-Clinical Research Ethics on Human Participants” so that I can make sure I adhere to it during my project | #1 | 1 | Lowest |  | Ethics
As a researcher, I want to see the status of my submitted ethics application, so I can rest assured that the process is underway. | #22 | 3 | Lowest |  | Ethics